## ENGLISH SUMMARY OF THE PROJECT

- Project title and location:

Counselling-Mediation and Monitoring Centre for the support of school-leavers and graduates in job placement process

- Brief project description:

Objectives:

Ensuring balance on the regional labour market between required and transferable skills on one side and of school –leavers and graduates' profiles on the other side.

Job placements and the enhancement of employability of school-leavers and graduates (further SLGs) in pilot districts Banska Bystrica and Brezno

Scope of support:

Project is focused on addressing the University graduates, secondary and vocational schools’ leavers unemployment in pilot districts Banska Bystrica and Brezno. There were partners – important organisations and bodies such as Banska Bystrica Regional Self-government (RSG) Office, Faculty of Economics of the Matej Bell University, District Labour Offices (DLO) in Banska Bystrica and Brezno and the Software Company GAMO included into the project’s preparation. Selected activities will be realised by experts in the field of sociology, marketing, psychology, management and adult’s education. The establishment of the Counselling-Mediation and Monitoring Centre with its detached branches at Banska Bystrica and Brezno DLOs is also the project’s component. These will ensure project’s activities such as provision of counselling and mediation services for SLGs and Employers not only during the project life but also after its end. To keep this idea sustainable the experts will develop databases of unemployed SLGs in pilot districts, of potential employers in Slovakia and a database of  training and retraining courses that are suitable for this target group. Project will work with the target group by various ways. Part of unemployed SLGs that will meet criteria will be placed directly into jobs, some will be placed into SLGs’ practice scheme, selected group will pass through motivation programmes, training courses for computer skills (based on actual needs of trainees and employers) and another selected group will take in courses focused on self-employment. The remaining part of SLGs and SLGs with special interest will take individual counselling programmes. All of above mentioned activities will form Action Plans’ components that will be developed by SLGs with the expert’s assistance.

Regional impact:

Counselling, mediation and monitoring capacity in the county for unemployed  will be improved. Considerable part of unemployed SLGs in pilot districts Banska Bystrica and Brezno  will take in motivation and retraining courses and will be placed either in jobs or in SLG’s practice scheme. Databases developed within the project will enhance the quality as well as speed up the counselling and mediation work of district labour offices after databases have been disseminated and used.

Enhancement of Banska Bystrica county’s absorption capacity for the ESF will be also another important impact in the region

Expected results/ impact:

Counselling-Mediation and Monitoring centre established at the BB RSG Office and its two detached branches at the District Labour Office (DLO) BB and DLO Brezno.

Database of  SLGs in pilot districts, employers having vacant jobs and interest for SLG’s practice as well as database of available retraining courses developed and updated.

Individual action plans of SLG’s for labour market placement developed, part of SLGs placed directly into jobs and another part into school leavers practice scheme

Motivation and retraining courses for SLGs realised with emphasis on development of key qualifications, transferable skills and preparation for self-employment.

- Budget (in EUR):

Total budget (including any co– financing)                       49 034,-        EUR

4. Project implemented in partnership:			             YES

- Project beneficiary:

Project manager:		Ing. Rudolf Gízel

Project co–ordinator :	Mgr. Daniela Haragová

Name of organisation:  	 Office of the Regional Selfgovernment Banska Bystrica

Name of representative:  	Prof. RNDr. Milan Marcok, DrSc

Function:		Chairman

Address:		Nám. SNP 23,   974 01   Banská Bystrica, Slovak Republic

tel. 048 4325638

email: rgizel@vucbb.sk